- WINNET 8

- Portugal Action Plan (AP):

Regional Action Plan for implement in Portugal, in Alentejo Central region, a Women's Resource Centre (WRC).

- The region: Alentejo Central / Portugal

- The Vision for the Action Plan:

Until 2012, have in Alentejo Central, a Resource Centre for Employment, Entrepreneurship and Gender Equality, working for the promotion of gender equality, promotion of female entrepreneurship and increasing skills in new technologies and innovation.

- General objectives and purpose of the Action Plan:

Implement a Centre for Employment, Entrepreneurship and Gender Equality, in Alentejo Central, this being a service of Monte and its five partners, conducted in partnership with other agencies, with the central objective to contribute to regional growth and increased participation of women in the labour market, reinforcing skills in the areas of entrepreneurship, innovation and new information technologies, by offering consultancy services, specific training and monitoring, combined with financial support (micro credit)  and support needs, related to gender (psychological support, legal advice, etc.).

- Description of the present situation in connection to the objectives of the AP:

- SWOT Analyses of the region (ANNEX I)

Alentejo is one of the five continental regions of Portugal, consisting of the following sub-regions:

- Alto Alentejo;

- Alentejo Central;

- Baixo Alentejo;

- Alentejo Litoral;

- Lezíria do Tejo.

The main positive characteristics of this region are:

- High standards of environmental quality;

- Competitive urban systems and productive sectors;

- Promising potentialities.

Alentejo is the largest level II territorial unit - NUTS II – in Portugal, occupying an overall area of 27,276.71 km², which represents 29.6% of the national territory.

The resident population in the region was, in 2009, of 753,407 inhabitants, 7.4% of the total population of Continental Portugal (Table 1), distributed over an area equivalent to one third of the country. This being the region with the lowest population density in Portugal - about 20 inhabitants per km².

| Quadro 1 – População residente, segundo o sexo, por NUTS III em 31/12/2009 |  |  |  |
| --- | --- | --- | --- |
| Table 1 - Resident population according to sex, by NUTS III on 31/12/2009 |  |  |  |
| N.º | H (Male) | M (Female) | Total |
| Portugal Continental | 4 909 494 | 5 235 446 | 10 144 940 |
| Alentejo | 369 686 | 383 721 | 753 407 |
| Alentejo Litoral | 47 348 | 47 556 | 94 904 |
| Alto Alentejo | 56 000 | 59 421 | 115 421 |
| Alentejo Central | 82 078 | 86 038 | 168 116 |
| Baixo Alentejo | 61 903 | 63 163 | 125 066 |
| Lezíria do Tejo | 122 357 | 127 543 | 249 900 |
| Fonte: INE, I.P., Portugal, 2010, Anuário Estatístico da Região Alentejo 2009 Source: INE, I.P., Portugal, 2010, Statistical Yearbook of Alentejo Region 2009 |  |  |  |

Alentejo contributes with 4.6% of the Portuguese GDP:

- GDP indicator only 7% below national average;

- Alentejo Litoral with GPD above national average;

- Baixo Alentejo with the lowest GDP.

The tertiary sector plays the main role with 61,5% of GVA.

The secondary sector contributes with 24,8% of GVA.

The primary sector accounts for 13,7% of GVA.

The primary sector is still larger in Alentejo than in the rest of the country.

- Alentejo Litoral presents the highest productivity rate.

Small enterprises are the backbone of Alentejo 's business structure:

- 3/5 of enterprises are in the tertiary sector;

- 1/5 of enterprises are in the secondary sector;

- 1/5 of enterprises are in the primary sector.

In Baixo Alentejo and Alentejo Litoral 1/4 of enterprises are linked with agriculture and fishing.

Below are presented some data / statistical indicators concerning the situation of (un) employment in Portugal, in Alentejo region, and in some specific cases, in their Sub-Regions.

| Quadro 2 – Indicadores do mercado de trabalho por NUTS II, 2009 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Table 2 – Labour market indicators by NUTS II, 2009 |  |  |  |  |  |  |  |  |  |  |
| % | Taxa de desemprego / Unemployment rate |  |  | Proporção de desemprego de longa duração | Activos com pelo menos a escolaridade obrigatória no total da população | Quadros superiores e especialistas no total de empregados | Empregados no sector terciário no total de empregados | Empregados por conta de outrem no total de empregados | Empregados por conta própria no total de empregados | Inactivos por 100 empregados |
|  | Total | Mulheres | 15-24 anos |  |  |  |  |  |  |  |
| Portugal Continental | 9,6 | 10,3 | 20,2 | 46,5 | 43,9 | 16,3 | 60,3 | 76,0 | 23,1 | 99,8 |
| Alentejo | 10,5 | 11,9 | 23,6 | 40,0 | 43,1 | 15,7 | 64,5 | 81,1 | 17,7 | 117,9 |
|  | Unemployment rate |  |  | Long-term unemployment as a share of total unemployment | Active population with at least compulsory education completed as a share of total population | Legislators, senior officials, managers and specialized professionals as a share of total employment | Population employed in tertiary sector (services) as a share of total employment | Employees as a share of total employment | Self-employed persons as a share of total employment | Inactive population per 100 employees |
|  | Total | Female | 15-24 years |  |  |  |  |  |  |  |
| Fonte: INE, I.P., Portugal, 2010, Anuário Estatístico da Região Alentejo 2009 Source: INE, I.P., Portugal, 2010, Statistical Yearbook of Alentejo Region 2009 |  |  |  |  |  |  |  |  |  |  |

| Quadro 3 – Taxa de Actividade e Taxa de Emprego, segundo o Sexo, por NUTS II, 2009 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Table 3 – Activity and Employment rate, according to sex by NUTS II, 2009 |  |  |  |  |
| % | Taxa de actividade / Activity rate |  | Taxa de emprego / Employment rate |  |
|  | Homens / Male | Mulheres / Female | Homens / Male | Mulheres / Female |
| Portugal Continental | 57,2 | 48,2 | 62,0 | 50,4 |
| Alentejo | 54,3 | 43,2 | 57,2 | 43,5 |
| Fonte: INE, I.P., Portugal, 2010, Anuário Estatístico da Região Alentejo 2009 Source: INE, I.P., Portugal, 2010, Statistical Yearbook of Alentejo Region 2009 |  |  |  |  |

| Quadro 4 – População activa por NUTS II, segundo o nível de escolaridade completo e o sexo, 2009 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Table 4 – Active population by NUTS II and according to educational level completed and sex, 2009 |  |  |  |  |  |  |  |  |  |  |  |
| Unidade: milhares Unit: thousands | Total |  | Sem instrução | Básico - 1º Ciclo |  | Básico - 2º Ciclo |  | Básico - 3º Ciclo |  | Secundário | Superior |
|  | H | M | HM | H | M | H | M | H | M | HM | HM |
| Portugal Continental | 2 811,2 | 2 522,9 | 217,9 | 734,5 | 585,3 | 550,7 | 377,1 | 634,0 | 507,5 | 901,1 | 826,1 |
| Alentejo | 201,4 | 166,2 | 11,0 | 55,2 | 35,7 | 42,3 | 22,8 | 49,1 | 39,2 | 64,9 | 47,3 |
| Fonte: INE, I.P., Portugal, 2010, Anuário Estatístico da Região Alentejo 2009 Source: INE, I.P., Portugal, 2010, Statistical Yearbook of Alentejo Region 2009 |  |  |  |  |  |  |  |  |  |  |  |

| Quadro 5 – População empregada por NUTS II, segundo o sector de actividade principal (CAE Rev. 3) e o sexo, 2008 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Table 5 – Employed population by NUTS II and according to sector of main activity (NACE Rev. 2) and sex, 2008 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Unidade: milhares | Total |  |  | Primário CAE: A |  |  | Secundário CAE: B - F |  |  |  | Terciário CAE: G - U |  |  |  |
|  | HM | H | M | HM | H | M | HM | H | M | HM |  | H | M |  |
| Portugal Continental | 4 823,2 | 2 560,1 | 2 263,2 | 537,9 | 273,7 | 264,2 | 1 375,2 | 997,8 | 377,5 | 2 910,1 |  | 1 288,6 | 1 621,5 |  |
| Alentejo | 328,9 | 182,4 | 146,4 | 35,0 | 26,5 | 8,5 | 81,8 | 63,1 | 18,7 | 212,1 |  | 92,8 | 119,3 |  |
| Unit: thousands | Total |  |  | Primary NACE: A |  |  | Secondary NACE: B - F |  |  | Tertiary NACE: G - U |  |  |  |  |
|  | MF | M | F | MF | M | F | MF | M | F | MF |  | M | F |  |
| Fonte: INE, I.P., Portugal, 2010, Anuário Estatístico da Região Alentejo 2009 Source: INE, I.P., Portugal, 2010, Statistical Yearbook of Alentejo Region 2009 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Quadro 6 – Disparidade no ganho médio mensal por sexo, por NUTS III, no ano 2008 |  |
| --- | --- |
| Table 6 – Disparity in mean monthly earning by sex, by NUTS III, in the year 2008 |  |
| % | Disparidade no ganho médio mensal por sexo |
| Portugal Continental | 11,90 |
| Alentejo | 14,30 |
| Alentejo Litoral | 21,70 |
| Alto Alentejo | 13,10 |
| Alentejo Central | 11,40 |
| Baixo Alentejo | 12,00 |
| Lezíria do Tejo | 13,90 |
| Fonte: INE, I.P., Portugal, 2010, Anuário Estatístico da Região Alentejo 2009 Source: INE, I.P., Portugal, 2010, Statistical Yearbook of Alentejo Region 2009 |  |

| Quadro 7 – Beneficiários de subsídios de desemprego, segundo o sexo e idade, por NUTS III, 2009 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Table 7 – Recipients of unemployment benefit, according to sex and age, by NUTS III, 2009 |  |  |  |  |  |  |  |  |  |
| N.º | Total | Sexo |  | Idade |  |  |  |  |  |
|  |  | H | M | Menos de 25 anos | 25-29 anos | 30-39 anos | 40-49 anos | 50-54 anos | 55 e mais anos |
| Portugal Continental | 526 700 | 252 926 | 273 774 | 43 683 | 66 853 | 140 575 | 116 284 | 58 640 | 100 665 |
| Alentejo | 43 529 | 21 329 | 22 200 | 3 669 | 5 373 | 11 166 | 9 808 | 4 802 | 8 711 |
| Alentejo Litoral | 5 290 | 2 639 | 2 651 | 434 | 626 | 1 332 | 1 164 | 656 | 1 078 |
| Alto Alentejo | 6 855 | 3 413 | 3 442 | 573 | 887 | 1 759 | 1 577 | 752 | 1 307 |
| Alentejo Central | 9 244 | 4 466 | 4 778 | 887 | 1 227 | 2 539 | 2 075 | 918 | 1 598 |
| Baixo Alentejo | 7 176 | 3 576 | 3 600 | 596 | 856 | 1 808 | 1 683 | 791 | 1 442 |
| Lezíria do Tejo | 14 964 | 7 235 | 7 729 | 1 179 | 1 777 | 3 728 | 3 309 | 1 685 | 3 286 |
|  | Total | Sex |  | Age |  |  |  |  |  |
|  |  | M | F | Under 25 years | 25-29 years | 30-39 years | 40-49 years | 50-54 years | 55 years and over |
| Fonte: INE, I.P., Portugal, 2009, Anuário Estatístico da Região Alentejo 2009 Source: INE, I.P., Portugal, 2010, Statistical Yearbook of Alentejo Region 2009 |  |  |  |  |  |  |  |  |  |

- Identified challenges and development points

- What are they

Consist of overcome the following problems / obstacles:

- Weak entrepreneurial spirit and risk aversion;

- Stigmatization of failure;

- Low demand and sufficient supply in various areas of business;

- Lack of some support services in the early stages and in the phase of monitoring of business (financial advice, legal support, marketing and sales);

- Unknowing by potential entrepreneurs of services to support entrepreneurship;

- Insufficient articulation among promoting entities that support employability and job creation.

How they were identified: bibliographic research, direct observation, focus group performed by the MAG, interviews apply to key informants.

- Detailed objectives based on the general objective and on the identified challenges

  - Until December 2011, start the exchange of experiences and information at the level of methodologies and tools to support business creation and entrepreneurship;

  - Until May 2012 start the process of identification, appropriation and adaptation of methodologies to support business creation and entrepreneurship among women, applied to the regional context;

  - Until May 2012, create a Resource Centre for Employment, Entrepreneurship and Gender Equality (MONTE-ACE);

  - Until May 2012, establishing networks of cooperation between entrepreneurs from different regions in order to stimulate the exchange of experiences among enterprises managed or created by women, located in rural areas;

  - Until September 2012, start actions aimed the motivation for entrepreneurship of women unemployed or looking for their first job;

  - Until April 2013, reinforcing the knowledge / skills of the technicians of the partner institutions on entrepreneurship, particularly in areas of low population density with development problems;

  - Until April 2013, start training agents for the creation of enterprises and entrepreneurship;

  - Until April 2013, promote the mainstream of women entrepreneurship, in rural areas of intervention of the partner institutions;

  - Until April 2013, promote the internationalization of products and services through the European Network for Women's Resource Centre.

- Best Practice to be transferred to Portugal / Alentejo:

- Definitions and descriptions of the good practises to be transferred

Ergani Centre, Centre for the support of female employment and entrepreneurship - Women Resource Centre founded as an informal initiative at 1991 by public and private organizations, became an NGO at 2001. This Centre implements projects and actions in favour of women from north Greece.

- What we will transfer of this good practice - Ergani Centre:

Knowledge and experiences on the following thematic: as to promote feminine enterprise and associative spirit (case of success of the cooperatives); how to get properly informing and mobilizing the target audience; guiding and/or rendering of services directed for the women, such as, legal support, elaboration of candidacies the programs and measures, marketing and commercialization, formation, consultancy, support the customers.

- What form they will take and how their implementation will be evaluated

The transferring of this good practice will be conducted based on the work started in WINNET8 project (mapping from territory by the diagnosis, statistical information, a bibliography on the subject and report of the Study Visit to Greece and workshops conducted under this project), complemented by new monitoring visits (evaluated at the end of the initiative) and contacts at distance (evaluated with a periodicity to be established).

- Details on how the implementation will take place; description of the transfer process

Implementation will take place establishing a work program (approved in advance by all stakeholders), which should include:

1. Identification of existing practices in Ergani Center that can be adapted in Portugal (through the report of the Study Visit to Greece, held in the context of Winnet8 project, and new contacts at distance with this Centre);

2. Visit of a Portuguese delegation to Greece to collect relevant information in the local;

3. Start the implementation of the practices in Portugal, gathered in Greece;

4. Follow-up visit from Greece to Portugal, to monitor the work and provide advice to the work to develop in the next steps.

5. Regular contact distance for clarification of doubts and provide information considered relevant, to finalize the process of installation of the Women Resource Centre.

| Steps and tasks for meeting the objectives | Organisations; names and roles of the main stakeholders | Competences needed for carrying out the implementation | Funding | Expected obstacles of completing the tasks |
| --- | --- | --- | --- | --- |
| Realization of transnational applications (in partnership with Ergani Center) and national (in partnership with ADRACES), in order to collect information to provide quality services to users and also to obtain financing; | Ergani Center – Coaching; ADRACES - provide knowledge on female entrepreneurship; MONTE-ACE - develop and implement applications. | To be defined. | PRODER, subprogram 3, action 3.4.1 - Cooperation Interterritorial | Inexistence of applications in due time; Application not approved by insufficient budget. |
| Establishment of partnership with IEFP (Institute for Employment and Professional Training) for support measures to self-employment. Such as consulting, training and mentoring to entrepreneurs. Protocol already signed. Monte is awaiting the contact of IEFP and of potential entrepreneurs. | IEFP - subcontract Association Monte for developing the measures to support self-employment; Monte-ACE – provide technical support to potential entrepreneurs. | Monte-ACE: Competencies of the technical staff of the institution in the area of entrepreneurship (Defined in Ordinance n.º 985/2009, of September 4, as amended by Decree n.º 58/2011 of 28 January). | IEFP (subcontracts Monte, conditions established in Ordinance n.º 985/2009, of September 4, with the wording given by Decree n.º 58/2011 of 28 January). | No existence of Monitoring Plans (for lack of interest of the unemployed who choose to create their own employment). |
| Establishment / strengthening of partnerships with the Municipalities / Social Networks, in order to involve the Municipal Counsellors for Equality in the structure of the WRC, as facilitators of the contact between the WRC and institutions present in the Social Network and also with women themselves. This makes possible a greater adaptation of the WRC's activities to the instruments of local and national politics and also signalling the situations that require to be guided to the WRC; | Municipalities / Social Networks of Alentejo – facilitate a better adaptation of the WRC's activities to the instruments of local and national politics and also signalling the situations that require to be guided to the WRC; | Competencies of Municipal Councillors for Equality defined in Article 3rd of the Resolution of the Council of Ministers n.º 39/2010 of May 25. | The performance of functions of the Municipal Councillors for equality not confers any entitlement to remuneration. Being, however, the technical and logistical support appropriate to the exercise of their functions provided by the municipality (articles 5.º and 6.º of the Resolution of the Council of Ministers n.º 39/2010 of May 25). | Unwillingness by some municipalities to adhere to the requests to cooperate in the implementation of the WRC; |
| Articulation with the Commission for Citizenship and Gender Equality (CIG), through interventions in the field, some already in progress and others planned, aimed at the empowerment of NGOs to promote gender equality in the Alentejo; | CIG – gives empowerment of NGOs to promote gender equality in the Alentejo; | Defined in Article 7.º of the annex to Order n.º 15608/2009 of July 9. | Human Potential Operational Programme (POPH) - Axis 7, "Gender Equality", Typology of intervention n.º 7.3, "Technical and financial support to nongovernmental organizations". | Financial constraints. |

| Steps and tasks for meeting the objectives | Organisations; names and roles of the main stakeholders | Competences needed for carrying out the implementation | Funding | Expected obstacles of completing the tasks |
| --- | --- | --- | --- | --- |
| Articulation with the Local Contracts for Social Development (CLDS), existing (Évora and Zone of Marbles) or planned (Arraiolos and Portel) for the region, particularly with their offices to support entrepreneurship; | CLDS – provide information on ongoing activities and perform joint activities; | Technical competence of the offices to support entrepreneurship (defined in Point 3 of Rule VII of the Ordinance n.º 396/2007 of April 2, as amended by Decree n.º 285/2008 of 10 April) | Human Potential Operational Programme (POPH) - Axis 6, "Citizenship, Inclusion and Social Development ", Typology of intervention n.º 6.13 "Contracts for Social Development" | Financial constraints; Reducing of the number of offices with the termination of some CLDS now ongoing. |
| Definition of the place or places where the WRC will work, adjusted to the management model that will be defined (contracts with local entities), aimed a decentralization of its operations for higher proximity to the target audience and increase the capacity to act; | Associated partners of MONTE, IEFP, APF and others – give suggestions about the better location for the WRC; | Choice of selection criteria. | Not applicable. | Are not expected obstacles. |
| Creation of an advisory committee (of advice) for the WRC, formed by members of MAG, Municipal Counsellors for Equality and members of the Reflection Group on Women Entrepreneurship in Regions of Low Population Density promoted by CISA-AS; | Members of MAG, Municipal Counsellors for Equality and members of the Reflection Group on Women Entrepreneurship in Regions of Low Population Density promoted by CISA-AS – advice the responsible entities for the WRC on strategies and specific actions; | Curriculums demonstrating knowledge in the context of gender equality and / or entrepreneurship. | Not applicable. | Overcharge by MAG members and others stakeholders; Lack of interest in participating in activities for which they may be contacted. |
| Establishment of a partnership with the Association for Family Planning (APF) to provide psychological support services and conducting information campaigns and awareness in the context of gender equality. | APF - provide psychological support services and conducting information campaigns and awareness in the context of gender equality; | To be defined. | to be defined. | Unwillingness and / or overcharge by APF; |
| Establishment of a protocol with the Commission for Equality in Labour and Employment (CITE) , to decentralize some of its services. | Provide some services (to be defined) in the context of centre. | To be defined. | To be defined. | Unavailability and / or overcharge by CITE |

ANNEX I

SWOT ANALYSIS

STRENGTHS

- Entities in the region working on the Thematic (IEFP, ADRAL, GADE’s, CLDS’s, Delegations of the National Association for Microcredit and accredited entities to provide technical support to the creation and consolidation of Projects of PAECPE/IEFP);

- Local and regional media;

- Motivation of Some women for the creation of own business;

- Existence of some specific market niches (bakery, confectionery, salted cooking, some handicrafts, services at domicile – cleaning, health and wellness);

WEAKNESSES

- Low female associativism;

- Lack of monitoring and advice for female entrepreneurship;

- Unemployment rate is higher in females;

- Low educational and vocational qualification of a significant number of women;

- Low buying power of the population;

- Demand insufficient for certain businesses;

- Insufficient Information about programs to support entrepreneurship;

- Difficulty in conciliate family responsibilities with a business;

- Does not exist a listing of business alternatives that may be viable and attractive;

- Inexistence in the territory of an integrated procedure between organizations (networking) in order to attend and forwarding women entrepreneurs;

- Inexistence, in the territory, of a culture of Gender Equality and Citizenship, which promotes for further participation of males in the activities of private space and of female gender in working life / public life;

OPPORTUNITIES

- Policies / measures to support female entrepreneurship (InAlentejo, PNI, PNAI, POPH, PRODER, FAME, QREN);

- Work undertaken by the Commission for Citizenship and Gender Equality (CIG) and the Commission for Equality in Labour and Employment (CITE);

- Touristic Potential of the Alqueva Dam;

- Community Funding Programs that promote the sharing / dissemination of Good Practices on female entrepreneurship and Gender Equality;

- Technology Plan (spread of ICT in contact with Public Administration; for exemple: Company On the Spot; extension of Broadband);

THREATS

- Cultural issues (gender discrimination);

- Depopulation in many areas of the Alentejo Region – low population density;

- Geographical isolation and access roads in poor condition.

Ordinance n.º 58/2011 of 28 January, can be accessed through the link: http://juventude.gov.pt/Legislacao/Documents/Portaria_58_2011.pdf

Resolution of the Council of Ministers n.º 39/2010 of May 25 can be accessed through the link: http://www.apav.pt/portal/pdf/consel_igualdade.pdf

Order n.º 15608/2009 of July 9, can be accessed through the link: http://www.poph.qren.pt/upload/docs/eixos/D_15608_09_TI_7_3.pdf

May consult the Ordinance n.º 396/2007 of 2 April in: : http://www2.seg-social.pt/acessibilidade/preview_documentos.asp?r=15837&m=PDF;  and Ordinance n.º 285/2008 of 10 April by the link: http://www2.seg-social.pt/acessibilidade/preview_documentos.asp?r=18853&m=PDF

 In Alentejo: NERBE, Association MONTE, ADCMoura and ADTR.